## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2175-swen-261-10-d D
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | SK; 3/4/18; passed
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | SK; 3/4/18; passed
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | SK; 3/4/18; passed
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | SK; 3/4/18; passed
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | AA; 3/4/18; passed
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | SK; 3/4/18; passed
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | sK; 3/4/18; passed
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | AA; 3/4/18; passed
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | AA; 3/4/18; passed
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | AP; 3/4/18; passed
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | ZE; 3/4/18; passed
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | AP; 3/4/18; passed
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | ZE; 3/4/18; passed
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | AG; 3/4/18; passed
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | AG; 3/4/18; passed
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Fail | AP; 3/4/18; drop action results in buggy behavior due to bug in model implementation
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | AG; 3/4/18; passed
As a Player I want to start a game so that I can play checkers with an opponent. | Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  |  | Pass | AG; 4/1/18; pass
As a Player I want to be able to make a move so that the game progresses. | Given that I can make a move when I drag the piece to a valid space then the piece should move to that space. |  |  | Pass | AG; 4/1/18; pass
| Given that I have dragged a piece when I submit my move then the move is confirmed and the turn switches to my opponent. |  |  | Pass | AG; 4/1/18; pass
| Given that my opponent is done with their turn when they submit their move then my opponent's turn ends and mine begins. |  |  | Pass | AG; 4/1/18; pass
As a Player I want to be able to move according to King rules so that take full advantage of a King's movement. | Given It is my turn when I move a kinged piece then I can move the king forwards or backwards on the board. |  |  | Pass | AG; 4/1/18; pass
| Given it is my turn when I move a kinged piece then I can jump opponent pieces either forwards or backwards. |  |  | Pass | AG; 4/1/18; pass
As a Player I want to be able to perform a simple capture so that I can capture my opponent's pieces and make progress in the game. | Given it is my turn when I jump over an opponents piece then the captured piece should disappear from the board. |  |  | Pass | AG; 4/1/18; pass
| Given it is my turn when I jump over an opponents piece then the captured piece should disappear from the board. |  |  | Pass | AG; 4/1/18; pass
| Given that I can capture a piece when I try to make a different move that does not capture a piece then I should not be able to make that move. |  |  | Pass | AG; 4/1/18; pass
As a User I want to step a piece in a direction so that I can move my peaces across the board. | Given I am in a game when I drag a piece to a valid location then I expect my piece to step to that location. |  |  | Pass | AG; 4/1/18; pass
As a Player I want to be able to multi jump over my opponent's pieces so that I can capture their pieces. | Given that I can jump multiple pieces when I take that jump path then my piece will capture multiple opponent pieces. |  |  | Pass | AG; 4/1/18; pass
| Given that I can jump multiple pieces when I take that jump path then the jumped pieces will disappear from the board. |  |  | Pass | AG; 4/1/18; pass
As a Player I want to be able to backup a move so that I can make a different move. | Given a piece has moved to another space when I click "undo" then the piece moves back to its original space.
Given that I "undid" a move when I try to make a different valid move then I should be able to make that move.
Given that I have just promoted a piece to king when I undo the move then the piece should move back to its original position as a normal piece.
Given that I captured a piece when I undo the move then my piece moves back to its original position and the captured piece reappears on the board.
Given that I made multiple jumps when I undo the move then the last of the multiple jumps is undone.